## Table 1
Up to 12 months before
☐ | Set a date |  | ☐ | Find a wedding planner
☐ | Get inspiration and ideas (see Pinterest and inspiration board) |  | ☐ | Find a photographer
☐ | Decide on a wedding style |  | ☐ | Find a caterer
☐ | Set priorities |  | ☐ | Find a florist
☐ | Set budget |  | ☐ | Find a musician
☐ | Choose wedding party |  | ☐ | Find a wedding dress
☐ | Find a venue for ceremony and reception |  | ☐ | Order save the dates
☐ | Consider purchasing wedding insurance |  | ☐ | If desired, set up a wedding website
10 – 11 months before
☐ | Start looking for dresses and accessories for bride and bridal party |  | ☐ | Book a wedding planner
☐ | Reserve a venue for ceremony and reception |  | ☐ | Book a caterer
☐ | Book a photographer |  | ☐ | Decide on décor
☐ | Book a DJ/band |  | ☐ | Start making a guest list
☐ | Book a florist |  | ☐ | Research legal requirements for marriage in your state or country
9 - 10 months before
☐ | Plan a honeymoon |  | ☐ | Start looking for favors
☐ | Start looking for invitations and stationery (wedding invitations, menu cards, thank you notes) |  | ☐ | Choose dresses and accessories for bride and bridal party
☐ | Consider engagement photos or a pre- wedding photoshoot
7 – 8 months before
☐ | Find two hotels for guests coming from out of town |  | ☐ | Reserve tables, chairs, linens, and anything else the caterer is not taking care of
☐ | Create gift registries |  | ☐ | Reserve décor
☐ | Start deciding on hairstyle and makeup style |  | ☐ | Choose cake
☐ | Book an officiant |  | ☐ | Decide on menu
☐ | Begin thinking about wedding vows or readings for the ceremony (see free wedding vow generator on 101planners.com)
6 – 7 months before
☐ |  | Meet with officiant | ☐ | Book a florist
☐ |  | Book cake | ☐ | Book a musician
☐ |  | Schedule tastings | ☐ | Finalize a guest list
☐ |  | Decide on outfits for groomsmen | ☐ | Research and book transportation for guests if many are coming from out of town
4 – 5 months before
☐ |  | Choose flowers for reception, party, attendants, etc. | ☐ | Finalize a rehearsal dinner guest list
☐ |  | Order wedding cake | ☐ | Purchase or rent toasting flutes and serving pieces
☐ |  | Schedule dress fittings | ☐ | Purchase or make a guest book
☐ |  | Book honeymoon flights and hotels | ☐ | Order a flower basket
☐ |  | Book room for wedding night | ☐ | Buy a ring bearer pillow
☐ |  | Discuss and plan pre-wedding parties or events (like bachelor/bachelorette parties, bridal showers) | ☐ | Finalize any rental orders or adjustments
3 – 4 months before
☐ |  | Prepare playlists for DJ/band | ☐ | Order menu cards
☐ |  | Book rehearsal dinner venue | ☐ | Order wedding favors
☐ |  | Finalize reception menu | ☐ | Order rehearsal dinner invitations
3 months before
☐ |  | Finalize honeymoon plans | ☐ | Create RSVP list
☐ |  | Ensure passport is valid if honeymoon is abroad | ☐ | Book spa and beauty treatments for you and your bridal party for week before
☐ |  | Plan ceremony | ☐ | Plan reception seating
☐ |  | Experiments with hair to decide on hairstyle | ☐ | Book mani/pedi/massage for day before
2 months before
☐ |  | Send wedding invitations | ☐ | Get "Something Old, New, Borrowed, Blue"
☐ |  | Update RSVP list | ☐ | Order transportation for wedding day
☐ |  | Begin writing wedding vows | ☐ | Pick up wedding rings
☐ |  | Meet with officiant to plan the ceremony | ☐ | Buy shoes and undergarments
☐ |  | Apply for marriage license | ☐ | Finalize playlists with DJ/band
☐ |  | Finalize fittings for wedding dress and wedding party | ☐ | Create a wedding day schedule and send to wedding party, vendors and officiant
☐ |  | Finalize seating | ☐ | Consider preparing a welcome bag for out-of-town guests
1 month before
☐ |  | Give a copy of your honeymoon itinerary to someone at home | ☐ | Call vendors to confirm date, time and location
☐ |  | Confirm honeymoon reservations | ☐ | Update registries
☐ |  | Pick up marriage license | ☐ | Delegate someone to return all rentals
☐ |  | Consider a teeth-whitening procedure if desired | ☐ | Provide any specific song requests for special moments (e.g., father- daughter dance, bouquet toss)
2 weeks before
☐ |  | Pack for honeymoon | ☐ | Prepare payments for vendors
☐ |  | Final dress fitting | ☐ | Prepare cash tips for service providers
☐ |  | Follow up with guests who have not RSVP'd | ☐ | Meet with photographer to discuss requests
☐ |  | Give caterer the final count | ☐ | Break in wedding shoes
☐ |  | Prepare wedding day emergency kit | ☐ | Send playlists to DJ/band
1 week before
☐ |  | Get haircut and color | ☐ | Get spa and beauty treatments for you and your bridal party
☐ |  | Prepare all wedding clothes
☐ |  | Confirm day-of timeline with all vendors | ☐ | Make any final adjustments with vendors
☐ |  | Prepare an overnight bag for the wedding night, if not returning home | ☐ | Ensure someone is designated to gather and keep safe gifts/cards from guests
☐ |  | Ensure someone is designated for vendor questions on the day, so you're not constantly approached with questions
The day before
☐ |  | Get a mani / pedi / massage | ☐ | Eat a good breakfast
☐ |  | Attend wedding rehearsal | ☐ | Give wedding rings to the best man
☐ |  | Wedding day
After the wedding
☐ |  | Return all rentals | ☐ | Send out thank you cards
☐ |  | Get wedding dress cleaned | ☐ | Get photos and video
☐ |  | Consider preserving the bouquet | ☐ | Review vendors online or provide testimonials if you were happy with their services
☐ |  | If changing your name, start the legal name change process